## Sheet1
Student | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Ashwin | As a User, I should be able to connect the parallel bars inside the square with any number of dots inside other shapes(triangle or Circle). | Knowledge gathering on java graphics and lines | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | revamp the class structure to connect the parallel bars inside the Square with Circle,Triangle | 0 | 2 | 1 | 1 | 0 | 0 | 0
|  | revamp the class structure to connect the parallel bars inside the Square with Square | 0 | 0 | 3 | 0 | 0 | 0 | 0
|  | Changes to the code to check whether a line is a part of a Square | 0 | 0 | 1 | 2 | 1 | 0 | 0
|  | Changes to check if the dot is an instance of the object | 0 | 0 | 0 | 0 | 2 | 1 | 0
|  | Test the changes to connect the bars inside the sqaure with any number of dots | 0 | 0 | 0 | 0 | 2 | 3 | 0
Ashutosh | As a User, I should be able to load the most recently saved state of the playground. | Knowledge Acquisition on De-Serializing Objects | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | Knowledge Acquisition on JMenu | 0 | 3 | 0 | 0 | 0 | 0 | 0
|  | Implementation of De-Serialization to the objects to load the recent state of the playground | 0 | 0 | 2 | 1 | 0 | 0 | 0
|  | Changes to be made to read the attributes of the object when loaded from the file | 0 | 0 | 2 | 2 | 0 | 0 | 0
|  | Reading the objects from a file in the root folder of the project | 0 | 0 | 0 | 2 | 1 | 0 | 0
|  | Test the changes of the loaded state of the playground | 0 | 0 | 0 | 0 | 3 | 1 | 0
Chandan | As a User, I should be able to save the current state of the playground. | Knowledge Acquisition on Serializing Objects | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Knowledge Acquisition on JMenu | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  | Implementation of Menu bar to the Jframe using JMenu | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | Implementation of Serialization to the objects to save the current state of the playground | 0 | 1 | 2 | 1 | 0 | 0 | 0
|  | Write the objects to a file in the root folder of the project | 0 | 0 | 2 | 2 | 0 | 0 | 0
|  | Test the changes of the saved state of the object | 0 | 0 | 0 | 1 | 2 | 0 | 0
Nachi | As a User, if I drag a shape, the lines connected to the shape should resize such that the newly formed structure has the same number of connections in place. | Knowledge gathering on java graphics, shapes and repaint | 3 | 1 | 0 | 0 | 0 | 0 | 0
|  | Changes to detect which shape is being selected upon drag | 1 | 3 | 0 | 0 | 0 | 0 | 0
|  | Code change to find all the lines present inside a particular shape | 0 | 2 | 2 | 1 | 0 | 0 | 0
|  | Fetch the co-ordinates of all the lines present inside the selected shape to drag | 0 | 0 | 2 | 2 | 1 | 0 | 0
|  | Update the co-ordinates of all the lines when the shape is released | 0 | 0 | 0 | 1 | 2 | 2 | 0
|  | Test the changes to check if the structure resizes after the shape is released. | 0 | 0 | 0 | 0 | 2 | 3 | 0
Srini | As a User, I need three dots in a triangle, one dot in a circle, two parallel bars inside a square. | Knowledge Acquistion on java Graphics | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implementation of add dot function to add dots inside the Circle and Triangle class | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | Changes to add two parallel bars inside a square | 0 | 1 | 1 | 0 | 0 | 0 | 0
Srini | As a User, I should be able to connect a dot inside a shape(triangle, circle) to a dot or bar on a different shape(triangle, circle or Square) only once. | Implementation of draw line functionality to connect two dots of a shape | 0 | 1 | 2 | 0 | 0 | 0 | 0
|  | Implementation of draw line functionality to draw many lines from a bar inside a rectangle | 0 | 0 | 0 | 3 | 0 | 0 | 0
|  | Code change to check only one line is drawn from a dot | 0 | 0 | 0 | 0 | 2 | 0 | 0
|  | Code change to check dots are not connected within a shape | 0 | 0 | 0 | 0 | 0 | 1 | 0