## Sheet1
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As a user, I should be able to see a dot at the center of the circle so that I can click on it. | Create a dot class and then add it in circle class | 0 | 1 | 0 | 0 | 0 | 0
As a user, I should be able to see three dots inside the triangle near the vertices so that I can click on them. | Add three instances of dots created in triangle class | 0 | 1 | 0 | 0 | 0 | 0
As a user, I should be able to see two vertical bars inside the square near the vertical sides so that I can click on them. | Create a vertical bar class and add it in square class | 0 | 1 | 0 | 0 | 0 | 0
As a user, I want to click on any shape on the left panel and then click on the right panel, so that I can see a copy of the clicked shape along with the dots or bars. | Saving mouse clicked shape from left panel | 0 | 1 | 0 | 0 | 0 | 0
| Copy saved shape to right panel | 0 | 1 | 0 | 0 | 0 | 0
As a developer I want to learn Graphics in Java Swing, so that I can apply that in the project. | Learn about graphics and how to draw various shapes | 2 | 0 | 0 | 0 | 0 | 0
| Check if we can use JavaFX to implement project easily. | 4 | 0 | 0 | 0 | 0 | 0
As a user, I should be able to click on a dot in one shape and another dot in another shape, inside right panel so that a line is drawn between them. | Add mouse click listener for dot class | 0 | 2 | 0 | 0 | 0 | 0
| Draw 2 lines between 2 dots | 0 | 2 | 0 | 0 | 0 | 0
As a user, I can move the shapes on the right panel so that the lines drawn between the dots or bars are still present. | Move all lines connected to dots | 0 | 2 | 3 | 3 | 1 | 0
| Move all lines connected to bars | 0 | 0 | 0 | 4 | 1 | 0
As a user, I should not be able to create multiple lines originating from one dot. | Check if a dot has a line connected and do not allow any more lines | 0 | 0 | 3 | 0 | 0 | 0
As a user, I can have multiple lines connecting a bar of the square. | Add mouse click listener for bar class | 0 | 0 | 0 | 2 | 0 | 0
| Allow multiple connections for bars | 0 | 0 | 0 | 3 | 0 | 0
As a developer I want to learn about mouse listeners in Java, so that I can apply that in the project. | Learn about mouse listeners to implement line connections and dragging shapes | 0 | 2 | 0 | 0 | 0 | 0
As a developer I want to learn file I/O operations in Java Swing, so that I can apply that in the project. | Learn how to save and load objects to files | 0 | 0 | 0 | 0 | 2 | 0
As a user, I want a graphical user interface split into 2 panels with a menu having save and open options. | Create a menu with 2 options and add it to the window created already. | 0 | 0 | 0 | 0 | 2 | 0
As a user, when I click on Save option from the Menu, contents of the right panel should be saved, so that I can retrieve it again. | Add action listener to save menu item | 0 | 0 | 0 | 0 | 1 | 0
| Save the connections and shapes arraylist in the right panel to file | 0 | 0 | 0 | 0 | 2 | 0
As a user, when I click on Open option from the Menu, I should be able to select a file to load the saved data. | Add action listener to load menu item | 0 | 0 | 0 | 0 | 1 | 0
| Load the connections and shapes arraylist from file and repaint everything | 0 | 0 | 0 | 0 | 2 | 0
[8 empty] | Days Remaining | 6 | 5 | 4 | 3 | 2 | 1
[8 empty] | Tasks Remaining | 21 | 21 | 11 | 10 | 8 | 0
[8 empty] | Ideal | 21 | 17 | 13 | 9 | 5 | 0