## Sheet1
Tasks/Days | Friday | Satuarday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
1. As a user, I want a frame with two panels and a menu to save and open a file.
a. Create a frame and add 2 panels. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Split panels Vertically. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Create a menu bar with 2 buttons Open and Save. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. As a user, I want a triangle with three dots at the top of the left panel.
a. Create a Button with triangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Create a Component with dot. | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
c. Add 3 dot components near each vertex. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
d. Add the triangle button at the top of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. As a user, I want a circle with a dot at the center at the middle of the left panel.
a. Create a Button with circle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add component with dot at the center of the circle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add the circle button at the middle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. As a user, I want a square with two vertical bars at the bottom of the left panel.
a. Create a Button with square shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Create Bars Component with bar shape. | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
c. Add 2 Bars Component. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
d. Add the square button at the bottom of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. As a user, I should be able to select any of the shape in left panel by clicking on it.
a. Add mouse click listener to triangle shape object. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add mouse click listener to circle shape object. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add mouse click listener to square shape object. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Store the instance of shape clicked in the static variable. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. As a user, I should be able to click in the right panel so that the selected shape in left panel is drawn at the clicked position.
a. Create a static variable to differentiate between shapes clicked. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add triangle, circle or square shape objects in the right panel at the position clicked based on the static variable’s value. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Create a prototype or proof of concept of dragging lines along with shapes and run tests on it.
a. Learn about mouse Listeners to drag a component inside panel. | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0
b. Create a prototype based on the knowledge acquired. | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
8. As a user, I should be able to drag any shape in the right panel.
a. Add mouse pressed listener to triangle shape object. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
b. Add mouse pressed listener to circle shape object. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
c. Add mouse pressed listener to square shape object. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
d. Study about static variables. | 0 | 0 | 0 | 1/2 | 0 | 0 | 0 | 0
e. Store the screen co-ordinates of the when mouse pressed event of the shape object occurs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f. Repaint the object component at the co-ordinates. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
9. As a user I should be able draw a line from dots.
a. Add mouse clicked listener to Dot component. | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the co-ordinates of the Dot component when clicked. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0
c. Study about drawing line. | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
c. Maintain a static variable to check if already clicked on Dot or Bar. | 0 | 1/2 | 1/2 | 0 | 0 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 4 | 3 | 3 | 3 | 2 | 2
10. As a user I should be able to draw lines from bars.
a. Add mouse clicked listener to Bar component. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
b. Store the co-ordinates of the Bar component when clicked. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
c. Maintain a static variable to check if Dot or a Bar is already clicked. | 0 | 0 | 0 | 0 | 1/2 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
11. As a system, I want any existing line to be dragged accordingly when any shape in right panel is dragged to a different position.
a. Store the new co-ordinates of the dragged shape and its dot and bar components. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
b. Repaint the line using new co-ordinates. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
12. Create a prototype or proof of concept of saving the co-ordinates of shapes and lines into a file and run tests on it.
a. Learn about FileWriter in java. | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
b. Create a prototype to write in the file. | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
13. Create a prototype or proof of concept of loading the co-ordinates of shapes and lines from a file and run tests on it
a. Learn about File Opening in java. | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
b. Create a prototype to read file contents appropriately. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
14. As a system, when user, clicks save, I should be able to save co-ordinates of all the shapes and lines in right panel into a file.
a. Add mouse click listener on Save button. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
b. Add FileChooser event to select the directory and file name. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add co-ordinates of shapes stored in right panel. | 0 | 0 | 0 | 3 | 4 | 0 |  | 3
15. As a system, when user, opens a saved file, I should be able to redraw the shapes and lines in the right panel.
a. Add mouse click listener on open button. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
b. Add FileChooser event to select the directory and file name. | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
c. Read co-ordinates of different shapes from the file and store it. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
d. Use the stored co-ordinates to repaint the shape objects. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Clean the code. | [7 empty] | 3